## Summary
|  |  | ❓ Tool Guidance |  | ❓ Glossary
Quality Tracker |  |  | Revert to |  |  | Currently Active |  |  | Activate
|  |  | << Stage -1 |  |  | Stage 0 |  |  | Stage 1 >>
26/61 answers
Overall Quality Statement: |  |  | Stage | Stage | Stage | Stage | Stage | Stage | Stage | Stage
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
active
click on the cells below to view or edit the risk levels of each stage
A | A1 | Land is in possession of commissioning client
| A2 | Client intends to deliver completed development
| A3 | Client intends to own and operate the completed building
Likelihood of Development Proceeding to Construction | A4 | Clearly defined end users and target markets included in brief
| A5 | All potential project stakeholders identified and engaged
| A6 | Comprehensive design team appointed
| A7 | Comprehensive background information supporting feasibility work
| A8 | High confidence of obtaining planning approval
| A9 | Planning application submitted at which RIBA workstage?
| A10 | All significant planning conditions have been discharged | 0: n/a
| A11 | Clearly defined sustainability objectives
| A12 | Fire safety analysis carried out | 0: n/a
| A13 | 0
| A14 | 0
| A15 | 0
| A16 | 0
| A17 | 0
| A18 | 0
| A19 | 0
| A20 | 0
B | B1 | OpEx carries significant weighting in tender scoring | 0: n/a
| B2 | Clerk of Works / independent inspector will be appointed
| B3 | Soft landings process implemented | 0: n/a
Attitude to Maintenance & Longevity | B4 | Warranty provider has active role in materials selection | 0: n/a
| B5 | As-built works and materials conform to Building Control approved drawings | 0: n/a
| B6 | FM team active in design decisions and commissioning process | 0: n/a
| B7 | FM team involved in POE process | 0: n/a
| B8 | POE includes user / occupier satisfaction survey | 0: n/a
| B9 | POE feedback acted upon | 0: n/a
| B10 | Defects rectified and validated | 0: n/a
| B11 | Exercise conducted on lessons learned from previous projects
| B12 | H&S issues identified and mitigated
| B13 | 0
| B14 | 0
| B15 | 0
| B16 | 0
| B17 | 0
| B18 | 0
| B19 | 0
| B20 | 0
C | C1 | Client's budget can accommodate cost increases if it adds value
| C2 | Project costs calculated cautiously per sqm and within budget
| C3 | Budget has been benchmarked against appropriate quality
Attitude to Cost Certainty | C4 | Adjustable Contract Sum (no GMP or NTE clauses) | 0: n/a
| C5 | ERs name products and materials in specification | 0: n/a
| C6 | Provisional sums constitute insignificant proportion of total budget
| C7 | Tenders are invited to make suitable allowance for contingencies | 0: n/a
| C8 | OpEx budget allowed for initial life of building (1-3 years) | 0: n/a
| C9 | OpEx for initial life of building (1-3 years) within budget | 0: n/a
| C10 | Contingency budget allowed for early teething problems (1-3 years) | 0: n/a
| C11 | Cost of early teething problems within budget | 0: n/a
| C12 | Design gap analysis completed for this stage (refer to checklist) | 0: n/a
| C13 | 0
| C14 | 0
| C15 | 0
| C16 | 0
| C17 | 0
| C18 | 0
| C19 | 0
| C20 | 0
D | D1 | Time to handover is not the most important factor
| D2 | Design programme allows for a comprehensive, iterative process
| D3 | Estimated construction programme considered comfortable
Attitude to Programme Certainty | D4 | Client shares risk for delays beyond the contractor's control | 0: n/a
| D5 | Key milestones relative to project start are not absolute
| D6 | Key programme issues are within control of client and project team
| D7 | Project plan consistent with planning and statutory constraints
| D8 | Project has financing support
| D9 | Project has end user and investor support
| D10 | 0
| D11 | 0
| D12 | 0
| D13 | 0
| D14 | 0
| D15 | 0
| D16 | 0
| D17 | 0
| D18 | 0
| D19 | 0
| D20 | 0
E | E1 | Straightforward construction methodology
| E2 | Tender packages unambiguous and comprehensively documented | 0: n/a
| E3 | ERs specify required quality of materials & workmanship
Likelihood of Obtaining Competitive Tenders | E4 | Design does not require significant subcontractor design input
| E5 | Project Lead accepts contractor's material substitutions obtained | 0: n/a
| E6 | Project team has engaged early with main contractors | 0: n/a
| E7 | Project team has engaged early with supply chain | 0: n/a
| E8 | Project team has identified key specialisms likely to be required
| E9 | 0
| E10 | 0
| E11 | 0
| E12 | 0
| E13 | 0
| E14 | 0
| E15 | 0
| E16 | 0
| E17 | 0
| E18 | 0
| E19 | 0
| E20 | 0
F | F1 | Collaborative approach to risk-sharing across team
| F2 | Design responsibility matrix coordinated between all parties
| F3 | Open-book arrangements on costs and margins
Attitude to Collaboration | F4 | Transparent methodology for allocating costs between parties
| F5 | Client shares responsibility for risks beyond contractor's control | 0: n/a
| F6 | Coordinated contractual arrangements between trade contractors | 0: n/a
| F7 | Partnering / alliancing contracts and integrated project insurance
| F8 | Project team has experience of working collaboratively
| F9 | 0
| F10 | 0
| F11 | 0
| F12 | 0
| F13 | 0
| F14 | 0
| F15 | 0
| F16 | 0
| F17 | 0
| F18 | 0
| F19 | 0
| F20 | 0

## Glossary
⬅ Back To Summary |  | ❓ Tool Guidance
Quality Tracker
Glossary
FM | Facilities Management
BC | Building Control
POE | Post Occupancy Evaluation
H&S | Health & Safety
GMP | Guaranteed Maximum Price
NTE | Not to Exceed
ERs | Employer's Requirements
NHBC | National House-Building Council
BCO | British Council for Offices
HTM | Health Technical Memoranda

## Stage (hidden)
| ⬅ Back To Summary | [9 empty] | ❓ Tool Guidance | ❓ Glossary
edit
Quality Custodians
| Quality Tracker | [9 empty] | Organisation | Representative
Client
Project Lead
| Stage 0 Strategic Definition | [5 empty] | Lead Designer
Contractor
TRUE | Project Name |  |  | Site Address | [6 empty] | copy details from Stage -1
26 | [6 empty] | Risk Status (26/61) |  |  |  | Reasoning
[7 empty] | click answer below |  |  |  | Brief explanation or reference to supporting material
0 | A | Likelihood of Development Proceeding to Construction | A1 | Land is in possession of commissioning client |  |  | yes | partly | no | n/a
0 |  |  | A2 | Client intends to deliver completed development |  |  | yes | partly | no | n/a
0 | If there is a high degree of confidence about the final outcome, early investment in a rigorous design process should yield a more robust solution with cost and programme benefits later on. Where there is limited confidence in the final outcome, the client will want to limit upfront expenditure. But if pre-planning design & survey costs are minimised, this increases the likelihood of post-planning redesign with associated implications on cost and programme. |  | A3 | Client intends to own and operate the completed building |  |  | yes | partly | no | n/a
0 |  |  | A4 | Clearly defined end users and target markets included in brief |  |  | yes | partly | no | n/a
0 |  |  | A5 | All potential project stakeholders identified and engaged |  |  | yes | partly | no | n/a
0 |  |  | A6 | Comprehensive design team appointed |  |  | yes | partly | no | n/a
0 |  |  | A7 | Comprehensive background information supporting feasibility work |  |  | yes | partly | no | n/a
0 |  |  | A8 | High confidence of obtaining planning approval |  |  | yes | partly | no | n/a
0 |  |  | A9 | Planning application submitted at which RIBA workstage? |  |  | End St 3 | Mid St 3 | St 2 | n/a
4 |  |  | A10 | All significant planning conditions have been discharged |  |  | yes | partly | no | n/a
0 |  |  | A11 | Clearly defined sustainability objectives |  |  | yes | partly | no | n/a
4 |  |  | A12 | Fire safety analysis carried out |  |  | yes | partly | no | n/a
0 |  |  | A13 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | A14 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | A15 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | A16 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | A17 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | A18 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | A19 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | A20 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | 0 | + Add Risk Indicator
0 |  |  | 0 | 0
4 | B | Attitude to Maintenance & Longevity | B1 | OpEx carries significant weighting in tender scoring |  |  | yes | partly | no | n/a
0 |  |  | B2 | Clerk of Works / independent inspector will be appointed |  |  | yes | partly | no | n/a
4 | Clients who take a hands-off approach towards the specification of products and materials can expect competitive tenderers to price for the lowest cost alternatives on the market. Adopting a project costing methodology that takes into account both CapEx & OpEx (with suitable gearing) enables products, materials and workmanship to be specified on the basis of quality and durability as well as cost. |  | B3 | Soft landings process implemented |  |  | yes | partly | no | n/a
4 |  |  | B4 | Warranty provider has active role in materials selection |  |  | yes | partly | no | n/a
4 |  |  | B5 | As-built works and materials conform to Building Control approved drawings |  |  | yes | partly | no | n/a
4 |  |  | B6 | FM team active in design decisions and commissioning process |  |  | yes | partly | no | n/a
4 |  |  | B7 | FM team involved in POE process |  |  | yes | partly | no | n/a
4 |  |  | B8 | POE includes user / occupier satisfaction survey |  |  | yes | partly | no | n/a
4 |  |  | B9 | POE feedback acted upon |  |  | yes | partly | no | n/a
4 |  |  | B10 | Defects rectified and validated |  |  | yes | partly | no | n/a
0 |  |  | B11 | Exercise conducted on lessons learned from previous projects |  |  | yes | partly | no | n/a
0 |  |  | B12 | H&S issues identified and mitigated |  |  | yes | partly | no | n/a
0 |  |  | B13 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | B14 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | B15 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | B16 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | B17 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | B18 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | B19 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | B20 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | 0 | + Add Risk Indicator
0 |  |  | 0 | 0
0 | C | Attitude to Cost Certainty | C1 | Client's budget can accommodate cost increases if it adds value |  |  | yes | partly | no | n/a
0 |  |  | C2 | Project costs calculated cautiously per sqm and within budget |  |  | yes | partly | no | n/a
0 | Where the budget can vary as the brief is developed, it may be acceptable to maintain an indicative cost plan based on area measurements. This will permit greater design flexibility during the early stages. If there is a fixed budget and no flexibility to vary the brief, it is important to establish an accurate cost plan using sophisticated estimating techniques, otherwise the project could reach an advanced stage of design and suddenly encounter viability problems. |  | C3 | Budget has been benchmarked against appropriate quality |  |  | yes | partly | no | n/a
4 |  |  | C4 | Adjustable Contract Sum (no GMP or NTE clauses) |  |  | yes | partly | no | n/a
4 |  |  | C5 | ERs name products and materials in specification |  |  | yes | partly | no | n/a
0 |  |  | C6 | Provisional sums constitute insignificant proportion of total budget |  |  | yes | partly | no | n/a
4 |  |  | C7 | Tenders are invited to make suitable allowance for contingencies |  |  | yes | partly | no | n/a
4 |  |  | C8 | OpEx budget allowed for initial life of building (1-3 years) |  |  | yes | partly | no | n/a
4 |  |  | C9 | OpEx for initial life of building (1-3 years) within budget |  |  | yes | partly | no | n/a
4 |  |  | C10 | Contingency budget allowed for early teething problems (1-3 years) |  |  | yes | partly | no | n/a
4 |  |  | C11 | Cost of early teething problems within budget |  |  | yes | partly | no | n/a
4 |  |  | C12 | Design gap analysis completed for this stage (refer to checklist) |  |  | yes | partly | no | n/a
0 |  |  | C13 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | C14 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | C15 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | C16 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | C17 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | C18 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | C19 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | C20 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | 0 | + Add Risk Indicator
0 |  |  | 0 | 0
0 | D | Attitude to Programme Certainty | D1 | Time to handover is not the most important factor |  |  | yes | partly | no | n/a
0 |  |  | D2 | Design programme allows for a comprehensive, iterative process |  |  | yes | partly | no | n/a
0 | Where the date for planning approval or for practical completion and handover are critical, quality may need to be a secondary or tertiary consideration. Quality is also at risk where land acquisition, or other agreements are conditional on planning approval being achieved within restricted timescales and incomplete design team appointments. Positive indicators include procurement strategies and allowance for early contractor engagement during the tendering period. |  | D3 | Estimated construction programme considered comfortable |  |  | yes | partly | no | n/a
4 |  |  | D4 | Client shares risk for delays beyond the contractor's control |  |  | yes | partly | no | n/a
0 |  |  | D5 | Key milestones relative to project start are not absolute |  |  | yes | partly | no | n/a
0 |  |  | D6 | Key programme issues are within control of client and project team |  |  | yes | partly | no | n/a
0 |  |  | D7 | Project plan consistent with planning and statutory constraints |  |  | yes | partly | no | n/a
0 |  |  | D8 | Project has financing support |  |  | yes | partly | no | n/a
0 |  |  | D9 | Project has end user and investor support |  |  | yes | partly | no | n/a
0 |  |  | D10 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D11 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D12 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D13 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D14 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D15 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D16 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D17 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D18 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D19 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | D20 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | 0 | + Add Risk Indicator
0 |  |  | 0 | 0
0 | E | Likelihood of Obtaining Competitive Tenders | E1 | Straightforward construction methodology |  |  | yes | partly | no | n/a
4 |  |  | E2 | Tender packages unambiguous and comprehensively documented |  |  | yes | partly | no | n/a
0 | When tender documentation is comprehensive and there is a large pool of interchangeable competitors, there is less need to engage the supply chain early. Two-stage tendering is useful if the project requires specialist construction techniques (eg offsite systems). By getting early engagement from the supply chain, the design can be tailored to the system and more accurate costs established. |  | E3 | ERs specify required quality of materials & workmanship |  |  | yes | partly | no | n/a
0 |  |  | E4 | Design does not require significant subcontractor design input |  |  | yes | partly | no | n/a
4 |  |  | E5 | Project Lead accepts contractor's material substitutions obtained |  |  | yes | partly | no | n/a
4 |  |  | E6 | Project team has engaged early with main contractors |  |  | yes | partly | no | n/a
4 |  |  | E7 | Project team has engaged early with supply chain |  |  | yes | partly | no | n/a
0 |  |  | E8 | Project team has identified key specialisms likely to be required |  |  | yes | partly | no | n/a
0 |  |  | E9 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E10 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E11 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E12 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E13 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E14 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E15 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E16 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E17 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E18 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E19 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | E20 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | 0 | + Add Risk Indicator
0 |  |  | 0 | 0
0 | F | Attitude to Collaboration | F1 | Collaborative approach to risk-sharing across team |  |  | yes | partly | no | n/a
0 |  |  | F2 | Design responsibility matrix coordinated between all parties |  |  | yes | partly | no | n/a
0 | Contractual arrangements that allocate risk exclusively to individual parties and take an adversarial approach to dispute resolution, are not likely to engender a collaborative response between the team members. When complex problems arise involving multiple parties, the first response will be to act defensively and seek to deflect blame. |  | F3 | Open-book arrangements on costs and margins |  |  | yes | partly | no | n/a
0 |  |  | F4 | Transparent methodology for allocating costs between parties |  |  | yes | partly | no | n/a
4 |  |  | F5 | Client shares responsibility for risks beyond contractor's control |  |  | yes | partly | no | n/a
4 |  |  | F6 | Coordinated contractual arrangements between trade contractors |  |  | yes | partly | no | n/a
0 |  |  | F7 | Partnering / alliancing contracts and integrated project insurance |  |  | yes | partly | no | n/a
0 |  |  | F8 | Project team has experience of working collaboratively |  |  | yes | partly | no | n/a
0 |  |  | F9 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F10 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F11 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F12 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F13 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F14 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F15 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F16 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F17 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F18 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F19 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | F20 | 0 | ✎ |  | yes | partly | no | n/a
0 |  |  | 0 | + Add Risk Indicator
|  | Role |  | Signed |  | Date |  |  |  |  | Representative | Organisation
|  | Client | [8 empty] | 0 | 0
|  | Project Lead | [8 empty] | 0 | 0
|  | Lead Designer | [8 empty] | 0 | 0
|  | Contractor | [8 empty] | 0 | 0

## data (hidden)
ActiveStage |  | 0 | [5 empty] | Strategic Definition | Preparation & Brief | Concept Design | Developed Design | Technical Design | Construction | Handover & Close Out | In Use
ViewStage |  | 0 | [5 empty] | org | [7 empty] | representative
Project Name
Site Address
Client
Project Lead
Lead Designer
61 | [6 empty] | Contractor
Show | InitialShw |  |  | yes | partly | no | n/a | 26 | 18 | 14 | 8 | 12 | 20 | 36 | 49 | comment | aplicability
TRUE | TRUE | A1 | Land is in possession of commissioning client | yes | partly | no | n/a | [5 empty] | 4 | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
TRUE | TRUE | A2 | Client intends to deliver completed development | yes | partly | no | n/a | [5 empty] | 4 | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
TRUE | TRUE | A3 | Client intends to own and operate the completed building | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | A4 | Clearly defined end users and target markets included in brief | yes | partly | no | n/a |  |  |  |  | 4 | 4 | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
TRUE | TRUE | A5 | All potential project stakeholders identified and engaged | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | A6 | Comprehensive design team appointed | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | A7 | Comprehensive background information supporting feasibility work | yes | partly | no | n/a |  |  |  | 4 | 4 | 4 | 4 | 4 |  | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
TRUE | TRUE | A8 | High confidence of obtaining planning approval | yes | partly | no | n/a |  |  |  |  | 4 | 4 | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
TRUE | TRUE | A9 | Planning application submitted at which RIBA workstage? | End St 3 | Mid St 3 | St 2 | n/a |  |  |  |  | 4 | 4 | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
TRUE | TRUE | A10 | All significant planning conditions have been discharged | yes | partly | no | n/a | 4 | 4 | 4 |  |  |  |  | 4 |  | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | A11 | Clearly defined sustainability objectives | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | A12 | Fire safety analysis carried out | yes | partly | no | n/a | 4 | 4 | [5 empty] | 4 |  | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
FALSE | FALSE | A13 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | A14 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | A15 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | A16 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | A17 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | A18 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | A19 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | A20 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE |  | BREAK | [13 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[17 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | B1 | OpEx carries significant weighting in tender scoring | yes | partly | no | n/a | 4 | 4 | 4 |  |  |  | 4 | 4 |  | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | B2 | Clerk of Works / independent inspector will be appointed | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | B3 | Soft landings process implemented | yes | partly | no | n/a | 4 | 4 | [7 empty] | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | B4 | Warranty provider has active role in materials selection | yes | partly | no | n/a | 4 |  |  |  |  | 4 | 4 | 4 |  | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
TRUE | TRUE | B5 | As-built works and materials conform to Building Control approved drawings | yes | partly | no | n/a | 4 | 4 | 4 | 4 | 4 |  |  | 4 |  | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE
TRUE | TRUE | B6 | FM team active in design decisions and commissioning process | yes | partly | no | n/a | 4 | 4 | [5 empty] | 4 |  | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | B7 | FM team involved in POE process | yes | partly | no | n/a | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
TRUE | TRUE | B8 | POE includes user / occupier satisfaction survey | yes | partly | no | n/a | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
TRUE | TRUE | B9 | POE feedback acted upon | yes | partly | no | n/a | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
TRUE | TRUE | B10 | Defects rectified and validated | yes | partly | no | n/a | 4 | 4 | 4 | 4 | 4 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE
TRUE | TRUE | B11 | Exercise conducted on lessons learned from previous projects | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | B12 | H&S issues identified and mitigated | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | B13 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | B14 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | B15 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | B16 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | B17 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | B18 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | B19 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | B20 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE |  | BREAK | [13 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[17 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | C1 | Client's budget can accommodate cost increases if it adds value | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | C2 | Project costs calculated cautiously per sqm and within budget | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | C3 | Budget has been benchmarked against appropriate quality | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | C4 | Adjustable Contract Sum (no GMP or NTE clauses) | yes | partly | no | n/a | 4 | [5 empty] | 4 | 4 |  | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | C5 | ERs name products and materials in specification | yes | partly | no | n/a | 4 |  |  |  |  | 4 | 4 | 4 |  | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
TRUE | TRUE | C6 | Provisional sums constitute insignificant proportion of total budget | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | C7 | Tenders are invited to make suitable allowance for contingencies | yes | partly | no | n/a | 4 | 4 | 4 |  |  | 4 | 4 | 4 |  | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE
TRUE | TRUE | C8 | OpEx budget allowed for initial life of building (1-3 years) | yes | partly | no | n/a | 4 | [8 empty] | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | C9 | OpEx for initial life of building (1-3 years) within budget | yes | partly | no | n/a | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
TRUE | TRUE | C10 | Contingency budget allowed for early teething problems (1-3 years) | yes | partly | no | n/a | 4 | [8 empty] | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | C11 | Cost of early teething problems within budget | yes | partly | no | n/a | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
TRUE | TRUE | C12 | Design gap analysis completed for this stage (refer to checklist) | yes | partly | no | n/a | 4 |  |  |  |  | 4 | 4 | 4 |  | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
FALSE | FALSE | C13 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | C14 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | C15 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | C16 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | C17 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | C18 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | C19 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | C20 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE |  | BREAK | [13 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[17 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | D1 | Time to handover is not the most important factor | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | D2 | Design programme allows for a comprehensive, iterative process | yes | partly | no | n/a | [5 empty] | 4 | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
TRUE | TRUE | D3 | Estimated construction programme considered comfortable | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | D4 | Client shares risk for delays beyond the contractor's control | yes | partly | no | n/a | 4 | 4 | 4 |  |  |  |  | 4 |  | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | D5 | Key milestones relative to project start are not absolute | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | D6 | Key programme issues are within control of client and project team | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | D7 | Project plan consistent with planning and statutory constraints | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | D8 | Project has financing support | yes | partly | no | n/a | [5 empty] | 4 | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
TRUE | TRUE | D9 | Project has end user and investor support | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
FALSE | FALSE | D10 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D11 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D12 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D13 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D14 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D15 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D16 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D17 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D18 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D19 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | D20 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE |  | BREAK | [13 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[17 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | E1 | Straightforward construction methodology | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | E2 | Tender packages unambiguous and comprehensively documented | yes | partly | no | n/a | 4 | 4 |  |  |  |  | 4 | 4 |  | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | E3 | ERs specify required quality of materials & workmanship | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | E4 | Design does not require significant subcontractor design input | yes | partly | no | n/a | [6 empty] | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | E5 | Project Lead accepts contractor's material substitutions obtained | yes | partly | no | n/a | 4 | 4 | 4 |  |  |  | 4 | 4 |  | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE
TRUE | TRUE | E6 | Project team has engaged early with main contractors | yes | partly | no | n/a | 4 |  |  |  |  | 4 | 4 | 4 |  | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
TRUE | TRUE | E7 | Project team has engaged early with supply chain | yes | partly | no | n/a | 4 |  |  |  |  | 4 | 4 | 4 |  | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
TRUE | TRUE | E8 | Project team has identified key specialisms likely to be required | yes | partly | no | n/a |  |  |  |  | 4 | 4 | 4 | 4 |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | E9 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E10 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E11 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E12 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E13 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E14 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E15 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E16 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E17 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E18 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E19 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | E20 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE |  | BREAK | [13 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[17 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE | F1 | Collaborative approach to risk-sharing across team | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | F2 | Design responsibility matrix coordinated between all parties | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | F3 | Open-book arrangements on costs and margins | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | F4 | Transparent methodology for allocating costs between parties | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | F5 | Client shares responsibility for risks beyond contractor's control | yes | partly | no | n/a | 4 | 4 | 4 |  |  |  |  | 4 |  | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | F6 | Coordinated contractual arrangements between trade contractors | yes | partly | no | n/a | 4 | 4 | 4 |  |  |  |  | 4 |  | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | F7 | Partnering / alliancing contracts and integrated project insurance | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
TRUE | TRUE | F8 | Project team has experience of working collaboratively | yes | partly | no | n/a | [7 empty] | 4 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
FALSE | FALSE | F9 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F10 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F11 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F12 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F13 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F14 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F15 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F16 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F17 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F18 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F19 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
FALSE | FALSE | F20 |  | yes | partly | no | n/a | [9 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
TRUE | TRUE |  | BREAK | [13 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE